## UserStory1
User Stories -> | [5 empty] | Create initial Release Plan, how many sprints, what will be dates, duration, no of stories to develop in each sprint.
Story Id | As a User | I wish to | so that I can | Name of Developer / tester | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Efforts Planned / Story points | Actual Efforts | Status (Not Started / WIP / Verified / Done)
Story 1 | Academy | Purches Product | Purches faculty product(Classes)
Task 1 | Design and Develop WEB Page for list of all classes which are added by perticular faculty (accepted faculty request) which having Title , Fields :Live Classes : Price, Total Lectures, Days ,Time,More Information having month and date . Like,Question,share(Facebook,Twitter,G+) Having Add To Cart(Button) for Academy for purches Product(Classes). |  |  | Rupali | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 |  |  | Done
Task 2 | Live classes and virtual classes should display in recently added . |  |  | Madhukar | 2015-09-10 | 2015-09-10
Task 3 | All product have its Auto generated code by Faculty ,Aacdemy,Publish this combination Should Be maitain. |  |  | Suraj | 2015-09-10 | 2015-09-10
Task 4 | Design and Develop Popup for Cart which is display on all over site also user can drag over anywhere on screen . |  |  | Rupali | 2015-09-09 | 2015-09-09 |  |  |  |  | Done
Task 5 | Double click on Cart logo then list should be display on cart popup which product are added to cart should be display having following attributes: Fields :Live Classes : Price, Total Lectures, Days ,Time,More Information having month ,date and charges. Having Two buttons: A)Add another Product B)Place Order |  |  | Suraj | 2015-09-11 | 2015-09-11
Task 6 | Cart Popup have Two Tabs: A) Live/Virtual -> all live and virtual product list should display as per order of add product B)Online/Study Material-> all Online/Study Material list should display as per order of add product |  |  | Madhukar | 2015-09-11 | 2015-09-11
Task 7 | Each product should have delete button , Delete button should delete the product from cart |  |  | Suraj | 2015-09-14 | 2015-09-14
Task 8 | Cart popup Having Two buttons : A)Add another Product -> redirect to all product list page having virtual,online product list (classes) B)Place Order -> after click on this button shows the Sign In dialogue box . |  |  | Suraj | 2015-09-14 | 2015-09-14
Task 9 | After sign In Following 3 Tab Should display : A)Personal Info B)Payment Details |  |  | Suraj | 2015-09-14 | 2015-09-14
Task 10 | A)Personal : Your Name,Email Address,Contact Number,Pin Code,Address |  |  | Madhukar | 2015-09-14 | 2015-09-14
Task 11 | B)Payment Details : All Cart Details (Payment Gateway) |  |  | Madhukar | 2015-09-15
Acceptance Criteria 1 | Verify: All List Of product Should display in having respective product data verify:list will identify by cluster by virtual class,live class. |  |  | Madhukar
Acceptance Criteria 2 | Verify:All product sholud display therir auto Generated unique code |  |  | Suraj
Acceptance Criteria 3 | Verify : Add Cart Button Working Or Not |  |  | Madhukar
Acceptance Criteria 4 | Verfy :After Clicking Add To Cart Button Perticular Class Sholud Add In To The List . |  |  | Suraj
Acceptance Criteria 5 | Verfy: All Required Information Should Display On product List Which are Added In to cart |  |  | Madhukar
Acceptance Criteria 6 | Verify:Amount Details Should Display On popup |  |  | Suraj
Acceptance Criteria 7 | Verify :Onclick on Place OrderButton Should Open Sign In Popup If User is Not Sign In . |  |  | Madhukar
Acceptance Criteria 8 | Verify: Following Information Should Display Correct Amount Pay Now,Pay of your Center,Total |  |  | Suraj
Acceptance Criteria 9 | Verify : Personal Information Should Accepted Your name,Email Address,Contact Number,Pin Code,Address |  |  | Madhukar
Acceptance Criteria 10 | Verify :Your name filed should accept only characters |  |  | Suraj
Acceptance Criteria 11 | verify:Email Address Field Should be take Only proper Email Formate |  |  | Madhukar
Acceptance Criteria 12 | Verify:Contact Number Field Should be accept only 10 Digits Numbers |  |  | Suraj
Acceptance Criteria 13 | Verify:Pin Code accept valid Pin code |  |  | Madhukar
Acceptance Criteria 14 | Verify :Address accept only alph numeric |  |  | Suraj
Acceptance Criteria 15 | Verify :Your name filed should accept only characters |  |  | Madhukar
Acceptance Criteria 16 | if Verify Criteria fails show proper Error Message. |  |  | Suraj
Story 2 |  |  |  | Suraj