## Product BkLog Template
| Product backlog sheet |  | Total Hours | 1079 | Version : |  |  | Doc Version:1.2
| Project Name : EduSmart Website |  | Total Developement hours : | 148 | Update Date: |  |  | Updated Date:07/06/2015
| Duration : From Date: 01/06/2015 to Date: |  | Total Designing hours : 94 | 199
Sr.No | Story Id | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Status (Done / WIP / Not started / On Hold) | Rupali's Hours | Designing status | Remarks
1 |  | Database Design |  | 16 | H |  |  | Done
2 |  | Application framework Design ( Struts + Hibernate + Tiles) |  | 24 |  |  |  | Done
3 |  | Account Creation 1) Academy Account. 1.1 Create Academy Account. 1.2 email verification |  | 23 |  |  |  | Done | 15 | Done
|  | 2) Faculty Account. 2.1 Faculty account creation 2.2 email verification |  | 8 |  |  |  | Done
|  | 3) Student Account. 3.1 Create student account 3.1 email verification |  | 8 |  |  |  | Not started
|  | 4)Coaching center Account. 4.1 Create Coaching center 4.1 email verification |  | 8 |  |  |  | Not started
4 |  | Login 1)Academy Login |  | 4 |  |  |  | Done | 2 | Done
5 |  | Forgot Password |  | 8 |  |  |  | Not started
6 |  | Academy Account (Home Page) 1) cover-Pic(Banner) display |  | 5 |  |  |  | Done | 8 | Done
|  | 2)Banner change and display |  | 5 |  |  |  | Not started
|  | 4)Profile-pic change and display from db |  | 5 |  |  |  | Not started | 2 | Done
|  | 5) Account Settings | [5 empty] | Need to discuss
|  | 6) View by | [5 empty] | Need to discuss
|  | 7)search by location. |  | 5 |  |  |  | Not started
|  | 8)search by Name. |  | 5 |  |  |  | Not started
|  | 9) search by email |  | 5 |  |  |  | Not started
Left side bar
|  | 1)About | [6 empty] | 10 | Done
|  | a) Display Description from database |  | 5 |  |  |  | Done
|  | b)Display Map for perticular academy from database |  | 1 |  |  |  | Done
|  | c)Display Address,Contact Number,Email,Website |  | 1 |  |  |  | Done
|  | About reset functionality |  | 10
|  | Edit functionality of A)Description B)Address | [5 empty] | Done
|  | C) Map |  | 16 |  |  |  | Not started
123 |  | 2) Faculty a)Display all Faculty list with Name,Image b)Display Total Faculty (Count) |  | 10 |  |  |  | Done | 12 | Done
|  | c)When Click on Plus button add/Create faculty dialog box will open |  | 5 |  |  |  | Requirement is Change
|  | d)when click on any faculty then control goes to that faculty timeline |  | 7 |  |  |  | Not started
|  | e)Hide and show tab for Centre and student |  | 8 |  |  |  | Not started
|  | f)Menu will change as respective selected option |  | 8 |  |  |  | Not started
|  | g) when click on show all link,all faculty list on faculty page will display. |  | 8 |  |  |  | Not started
|  | 3) Coaching Centre a)Display all Centre list with Location,Image b)Display Total Centre (Count) |  | 10 |  |  |  | Done | 4 | Done
|  | c)When Click on Plus button add/Create centre dialog box will open |  | 5 |  |  |  | Requirement is Change
|  | d)when click on any centre then control goes to that centre timeline |  | 7 |  |  |  | Not started
|  | e)Hide and show tab for faculty and student |  | 8 |  |  |  | Not started
|  | f)Menu will change as respective selected option |  | 8 |  |  |  | Not started
|  | g) when click on show all link,all centr list on centre page will display. |  | 8 |  |  |  | Not started
|  | 4) Gallery a)Display all Photos from Gallery b)Display Total Centre (Count) |  | 16 |  |  |  | Not started | 6 | Done
|  | c)When Click on Plus button add photo/video will be display. |  | 16 |  |  |  | Not started
|  | d) when click on show all link,all photo/video list on Gallery page will display. |  | 12 |  |  |  | Not started
|  | e)Hide and show tab for faculty and student |  | 8 |  |  |  | Not started
|  | f)Menu will change as respective selected option |  | 8 |  |  |  | Not started
|  | 5) News/Announcement a) Display news list b) Display total news(count) |  | 16 |  |  |  | Done | 6 | Done
|  | c) show 3 news at a time,after few seconds show new slide of news. |  | 8 |  |  |  | Done
|  | d) when click on any particular news,control will redirect to news page and focus will be on that particular news. |  | 8 |  |  |  | WIP
|  | e) when click on plus button,Add News/Annoucement window will be generated. |  | 8 |  |  |  | Done
|  | f) when click on show all link,will be redirect to news page and news list will display. |  | 8 |  |  |  | Done
|  | g) Hide and show tab for faculty and student |  | 8 |  |  |  | Not started
|  | h) Menu will change as respective selected option |  | 8
|  | 6) Upcoming Events a) Display all upcoming Event list b) display total upcoming Event(count) |  | 16 |  |  |  | Done | 6 | Done
|  | c) when click on any particular event,will be redirect to event page and focus will be on that particular event. |  | 5 |  |  |  | Not started
|  | d) when click on plus button,Add event window will be generated. |  | 4 |  |  |  | Done
|  | e) when click on show all link,will be redirect to event page and event list will display. |  | 8 |  |  |  | Done
|  | f) Hide and show tab for faculty and student |  | 8 |  |  |  | Not started
|  | h) Menu will change as respective selected option |  | 5 |  |  |  | Not started
|  | 7) Offers & Promotions a) Display all Offers & Promotions list b) Display total Offers & Promotions(count) |  | 16 |  |  |  | Not started | 4 | Done
|  | c) when click on any particular Offers & Promotions,will be redirect to Offers & Promotions page and focus will be on that particular Offers & Promotions. |  | 8 |  |  |  | Not started
|  | d) when click on plus button,Add Offers & Promotions window will be generated. |  | 6 |  |  |  | Not started
|  | e) when click on show all link,will be redirect to Offers & Promotions page and Offers & Promotions list will display. |  | 5 |  |  |  | Not started
|  | f) Hide and show tab for faculty and student |  | 6 |  |  |  | Not started
|  | g) Menu will change as respective selected option |  | 6 |  |  |  | Not started
|  | h) show 2 Offers & Promotions at a time,after few seconds show new slide of Offers & Promotions. |  | 8 |  |  |  | Not started
|  | 8) Reviews a) Display all reviews list b) Display total reviews (count) |  | 8 |  |  |  | Not started | 6 | Done
|  | c) when click on any particular Reviews,will redirect to Reviews page and focus will be on that particular Review. |  | 8 |  |  |  | Not started
|  | d) when click on plus button,Add Reviews window will be generated. |  | 5 |  |  |  | Not started
|  | e) when click on show all link,will redirect to Reviews page and Reviews list will display. |  | 5 |  |  |  | Not started
|  | f) show 2 Reviews at a time,after few seconds show new flash of Reviews. |  | 5 |  |  |  | Not started
|  | g) Rating will display between 1 to 5 star |  | 8 |  |  |  | Not started
|  | f) Hide and show tab for faculty and student |  | 4 |  |  |  | Not started
|  | g) Menu will change as respective selected option |  | 5 |  |  |  | Not started
|  | 9) Advertisement a) Display advertisement from DB b) |  | 5 |  |  |  | On Hold | 1 | Done
|  | 10) Display number of visits and current week visits(count). |  | 7 |  |  |  | Not started | 30 min | Done
|  | Header Bar 1) Title (Welcome to) will display with academy name,location from DB |  | 5 |  |  |  | Done | 30 min | Done
|  | 2) Logout when click on this button user logout. |  | 5 |  |  |  | Done | 10 min | Done
|  | 3) Messege a) display message from DB (count) |  | 6 |  |  |  | Done | 4 | Done
|  | b) Display message list from DB. |  | 5 |  |  |  | Done
|  | c)display message count ,when click on any particular message,will redirect to message page and focus will be on that particular message. |  | 8 |  |  |  | WIP
|  | e) Send new message |  | 8 |  |  |  | started
|  | 4) Notification a) display notification from DB (count) |  | 5 |  |  |  | Done | 4 | Done
|  | b) Display notification list from DB. |  | 4 |  |  |  | Done
|  | c) display notification count,when click on any particular notification,will redirect to notification page and focus will be on that particular notification. |  | 5 |  |  |  | WIP
|  | d) when click on show all link,redirect to notification page,display notification list. |  | 8 |  |  |  | Done
7 |  | Faculty Tab (Academy Timeline) 1 All Faculty (All Faculty list will display(diff. with our faculty and associated faculty) with their Profile pic,name, Course name(CA,CS,CMA),subject (Drop Down list)) |  | 8 |  |  |  | On Hold | 18 | Done
|  | a) Cart(Button) (when user will click on this button,he will redirect to product page and he will add product from here.) |  | 8
|  | b) Remove(Button) Remove particular faculty. |  | 5
|  | c) Suggest(Button) (if user wants to suggest someone about this faculty/recommend this faculty.) |  | 6
|  | d) subject drop down list. |  | 4
|  | e) notification |  | 5
|  | f) + friends drop down |  | 8
|  | 2 Recently Added (Display recently added faculty list) |  | 5 |  |  |  | On hold
|  | 3 Create Faculty (create a new faculty.) a) personal account info. (form) |  | 8 |  |  |  | Done
|  | b) faculty account info. (form) |  | 5 |  |  |  | Not started
|  | c) table designing |  | 4 |  |  |  | Done
|  | 4 Add Faculty (Faculty which is already in database,Academy will send a request through mail to join his Academy.) pop up will be generated with field like faculty name and email address. |  | 16 |  |  |  | Not started
|  | 5 Pending status (where Academy knows about pending request.) |  | 4 |  |  |  | Not started
|  | 6 CA (display Faculty of CA course will be display.) |  | 4 |  |  |  | Not started
|  | 7 CS (display Faculty of CS course.) |  | 4 |  |  |  | Not started
|  | 8 CMA (display Faculty of CMA course.) |  | 4 |  |  |  | Not started
8 |  | About Tab(Academy timeline) 1) Description a) Display academy description b) Posting will be deleted after 90 days |  | 5 |  |  |  | Done | 20 | Done
|  | b) Add description |  | 8 |  |  |  | Done
|  | c) edit description |  | 4 |  |  |  | Done
|  | d) reset description |  | 3 |  |  |  | Done
|  | e) delete description |  | 6 |  |  |  | Done
|  | f) like (count) |  | 6 |  |  |  | Done
|  | g) comment (count) write comment |  | 8 |  |  |  | Not started
|  | h) share using Facebook |  | 8 |  |  |  | Not started
|  | i) share using twitter |  | 8 |  |  |  | Not started
|  | j) share using g+ |  | 8 |  |  |  | Not started
|  | 2) Info a) Display Academey info. |  | 4 |  |  |  | Done
|  | b) Add info |  | 8 |  |  |  | Done
|  | c) edit Long Description, adress |  | 8 |  |  |  | Done
|  | d) share using Facebook |  | 8 |  |  |  | Not started
|  | e) share using twitter |  | 8 |  |  |  | Not started
|  | f) share using g+ |  | 8 |  |  |  | Not started
|  | 3) Member a) Display Member list. |  | 5 |  |  |  | Done
|  | b) Add member |  | 5 |  |  |  | Done
|  | c) edit member |  | 5 |  |  |  | Done
|  | d) reset member |  | 5 |  |  |  | Done
|  | e) delete member |  | 5 |  |  |  | Done
9 |  | News Tab (Academy Timeline) a) display News /Announcement list |  | 5 |  |  |  | Done | 18 | Done
|  | b) display News /Announcement list of last three months |  | 8 |  |  |  | Done
|  | c) display News /Announcement month wise |  | 5 |  |  |  | Done
|  | d) Add News /Announcement |  | 5 |  |  |  | Done
|  | e) edit News /Announcement |  | 5 |  |  |  | Done
|  | f) reset News /Announcement |  | 4 |  |  |  | Done
|  | e) delete News /Announcement |  | 5 |  |  |  | Done
|  | f) like (count) |  | 5 |  |  |  | Done
|  | g) comment (count) write comment |  | 7 |  |  |  | started
|  | h) share using Facebook |  | 8 |  |  |  | Not started
|  | i) share using twitter |  | 8 |  |  |  | Not started
|  | j) share using g+ |  | 8 |  |  |  | Not started
10 |  | Events Tab (Academy Timeline) a) display Events list |  | 5 |  |  |  | Done | 18 | Done
|  | b) display Events list of last three months |  | 8 |  |  |  | Done
|  | c) display Events month wise |  | 5 |  |  |  | Done
|  | d) Add Events |  | 8 |  |  |  | Done
|  | e) edit Events |  | 8 |  |  |  | Done
|  | f) reset Events |  | 5 |  |  |  | Done
|  | g) delete Events |  | 5 |  |  |  | Done
|  | i) like (count) |  | 5 |  |  |  | Done
|  | j) comment (count) write comment |  | 7 |  |  |  | started
|  | k) share using Facebook |  | 8 |  |  |  | Not started
|  | l) share using twitter |  | 8 |  |  |  | Not started
|  | m) share using g+ |  | 8 |  |  |  | Not started
11 |  | Gallery Tab(Academy TimeLine) a) Display Photos |  | 16 |  |  |  | Not started | 20 | Done
|  | b) Display videos |  | 8 |  |  |  | Not started
|  | c) Display Academy Timline Album |  | 5 |  |  |  | Not started
|  | d) Display News / Announcement Album |  | 8 |  |  |  | Not started
|  | e) Display Events Album |  | 5 |  |  |  | Not started
|  | f) Add Photo |  | 5 |  |  |  | Not started
|  | g) delete Photo |  | 5 |  |  |  | Not started
|  | h) Add Video |  | 8 |  |  |  | Not started
|  | i) Delete Video |  | 6 |  |  |  | Not started
|  | j) Create Album |  | 8 |  |  |  | Not started
12 |  | Reviews Tab(Academy Timeline) a) Display All Reviews list |  | 8 |  |  |  | Not started | 15 | Done
|  | b) like (count) |  | 5 |  |  |  | Not started
|  | c) Comment (count) |  | 2 |  |  |  | Not started
|  | d) Display count for 5 star |  | 8 |  |  |  | Not started
1079
|  |  |  | Total Hours | 1079 |  |  | 1079
|  |  |  | Total Developement hours : | 148 |  |  | 148
|  |  |  | Total Designing hours : 94 | 199 |  |  | 199

## Sprint1
Start Date:10/06/2015 To 17/05/2015(6 Days Working) |  | Sprint 1
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold)
| Academy pages integretion |  | 8 |  |  | Madhukar | 2015-10-06 | 2015-10-06 | Done
| Academy Registration a)email verification |  | 8 |  |  | Madhukar | 2015-11-06 | 2015-11-06 | Done
| Academy Login |  | 4 |  |  | Madhukar | 2015-12-06 | 2015-12-06 | Done
| Left side bar 1)About a)Display Description from database b)Display Map for perticular academy from database |  | 4 |  |  | Madhukar | 2015-12-06 | 2015-12-06 | Done
| Edit functionality of A)Description B)Address |  | 8 |  |  | Madhukar | 15/6/2015 | 15/6/2015 | Done
| 2) Faculty a)Display all Faculty list with Name,Image b)Display Total Faculty (Count) |  | 10 |  |  | Madhukar | 16/6/2015 | 17/6/2015 | Done
34

## Sprint2
Start Date:17/06/2015 To 24/05/2015(7 Days Working)
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold)
| Coaching Centre a)Display all Centre list with Location,Image b)Display Total Centre (Count) |  | 10 |  |  | Madhukar | 17/6/2015 | 18/06/15 | Done
| News Page Integretion |  | 8 |  |  | Madhukar | 18/06/15 | 19/06/15
| News/Announcement a) Display news list b) Display total news(count) |  | 16 |  |  | Madhukar | 19/06/15 | 22/06/15 | Done
| c) show 3 news at a time,after few seconds show new slide of news. |  | 8 |  |  | Madhukar | 22/06/15 | 23/06/15 | Done
| News Tab (Academy Timeline) a) display News /Announcement list |  | 5 |  |  | Madhukar | 23/06/15 | 24/06/15 | Done
| b) Add News /Announcement |  | 5 |  |  | Madhukar | 24/06/15 | 24/06/15 | Done
52

## Sprint3
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold)
| About Tab(Academy timeline) 1) Description a) Display academy description |  | 5 |  |  | Suraj | 29/07/2015 | 29/07/2015 | Done
| b) Add description |  | 4 |  |  | Suraj | 30/07/2015 | 30/07/2015 | Done
| 2) Info a) Display Academey info. |  | 5 |  |  | Suraj | 30/07/2015 | 30/07/2015 | Done
| b) Add info |  | 8 |  |  | Suraj | 2015-07-07 | 2015-07-07 | Done
| 3) Member a) Display Member list. |  | 5 |  |  | Suraj | 29/07/2015 | 29/07/2015 | Done
| b) Add member |  | 8 |  |  | Suraj | 2015-04-08 | 2015-04-08 | Done
| News Tab (Academy Timeline) a) display News /Announcement list |  | 5 |  |  | Suraj | 2015-01-07 | 2015-01-07 | Done
| d) Add News /Announcement |  | 8 |  |  | Suraj | 2015-02-07 | 2015-02-07 | Done
| f) reset News /Announcement |  | 5 |  |  | Suraj | 2015-03-07 | 2015-03-07 | Done

## Sprint4
Start Date: 06-jul-15 To 10-jul-15
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold)
| News Tab a) edit News /Announcement |  | 5 |  |  | Suraj | 2015-07-06 | 2015-07-06 | Done
| b) reset News /Announcement |  | 4 |  |  | Suraj | 2015-07-06 | 2015-07-07 | Done
| c) delete News /Announcement |  | 5 |  |  | Suraj | 2015-07-07 | 2015-07-07 | Done
| d) display News /Announcement list current news |  | 8 |  |  | Suraj | 2015-07-07 | 2015-07-08 | Done
| e) display News /Announcement past |  | 5 |  |  | Suraj | 2015-07-08 | 2015-07-08 | Done
| Event Tab a) display Events list of last three months |  | 8 |  |  | Suraj | 2015-07-08 | 2015-07-09 | Done
| b) display Events month wise |  | 5 |  |  | Suraj | 2015-07-09 | 2015-07-10 | Done
| Academy Post on Academy Timeline a) Add Post |  | 8 |  |  | Madhukar | 2015-07-06 | 2015-07-06 | Done
| b) display post |  | 5 |  |  | Madhukar | 2015-07-07 | 2015-07-07 | Done
| c) Add Events |  | 8 |  |  | Madhukar | 2015-07-07 | 2015-07-08 | Done
| d) display Events list |  | 5 |  |  | Madhukar | 2015-07-08 | 2015-07-08 | Done
Academy Post on Academy Timeline
| C) Edit post |  | 4 |  |  | suraj | 2015-07-09 | 2015-07-09 | Done
| d) reset post |  | 5 |  |  | suraj | 2015-07-09 | 2015-07-11 | Done
| e) delete post |  | 5 |  |  | Madhukar | 2015-07-11 | 2015-07-11 | Done
80

## Sprint5
|  |  |  | Sprint name: | 5 | 5
Start Date: 13-Jul-15 To 24-Jul-15
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold) | Priority | Client's comments
1) | News Tab a) like (count) |  | 5 | H |  | Suraj | 2015-07-13 | 13/07/2015 | Done |  | Okay
2) | b) comment (count) write comment |  | 7 | H |  | Suraj | 2015-07-13 | 14/07/2015 | Done |  | Okay
3) | 4) Notification a) display notification from DB (count) b) Display notification list from DB. |  | 7 | H |  | Suraj | 2015-07-15 | 2015-07-15 | Done |  | Okay
4) | Change Logic of Event And News Functionality as per Client Requirement. 1 Current News display for 30 days. 2 Past news display for 60 days. ​ 3 if user enter end date/due date ,then that date will be the end date ​ - in current news after that it will remain for 60 days in past news. Please correct likewise. ​ (90 days criteria will not apply 4 News will display most recent time wise. ​ |  | 6 | H |  | Suraj | 2015-07-17 | 2015-07-17 | Done |  | Okay
5) | Message Functionality a) Display message from DB (count) |  | 6 | H |  | Madhukar | 2015-07-15 | 2015-07-15 | Done |  | Okey
6) | b) Display message list from DB. |  | 5 | H |  | Madhukar | 2015-07-13 | 2015-07-14 | Done |  | Okey
7) | c)display message count ,when click on any particular message,will redirect to message page and focus will be on that particular message. |  | 8 | H |  | Suraj | 2015-07-14 | 2015-07-14 | Done |  | Okay
8) | e) Send new message |  | 7 | H |  | Madhukar | 2015-07-15 | 2015-07-15 | WIP |  | Okay
9) | C) Display notification count,when click on any particular notification,will redirect to notification page and focus will be on that particular notification. |  | 9 | H |  | Madhukar | 2015-07-16 | 2015-07-16 | Done |  | Okay
10) | Events Tab a) like (count) |  | 4 | H |  | Madhukar | 2015-07-17 | 2015-07-17 | Done |  | Okay
11) | b) comment (count) write comment |  | 4 | H |  | Suraj | 2015-07-17 | 2015-07-17 | WIP |  | Okay
12) | d) when click on show all link,redirect to notification page,display notification list. |  | 8 | H |  | Suraj | 2015-07-18 | 2015-07-18 | Done |  | Okay
13) | Create Faculty (create a new faculty.) - Logic Changed a bit a) personal account info. (form) - should be faculty profile and not in Academy profile |  | 5 | H |  | Suraj | 2015-07-20 | 2015-07-20 | Done | High | Please note this has been changed as per our last meeting dicussion. In Academy Profile - Faculty tab will have 3 sub main tabs 1. Faculty (Sort by CA, CS, CMA) 2. Add faculty (via DB Search) and 3. Pending Request (By Center & By Faculty) - Just like a center in Faculty Profile
14) | Recently Added - Priority low (Display recently added faculty list) |  | 8 | H |  | Suraj/Madhukar | 2015-07-20 | 2015-07-21 | Not started | Low | Priority is low. Hold this functionality
15) | b) faculty account info. (form) - should be faculty profile and not in Academy profile |  | 5 | H |  | Suraj | 2015-07-22 | 2015-07-22 | WIP | High | Okay - Note This tab should be in Faculty main profile
16) | c) Table designing (Faculty login, Add Faculty etc.) |  | 4 | H |  |  | 2015-07-22 | 2015-07-22 | Done |  | Not sure for what
17) | 4 Add Faculty (Faculty which is already in database,Academy will send a request through mail to join his Academy.) pop up will be generated with field like faculty name and email address. |  | 16 | H |  | Madhukar | 2015-07-20 | 2015-07-21 | Not started | High | Okay - When you click on add a faculty - window will pop up like compose box which will have fields like "To" - in this academy can search faculty from data base, 2nd field "Subject" - interested to associate with you (as a default subject which can be editable) and 3rd field - text box. This box may some predefined text or he can overwrite on it.
18) | Faculty Tab (Academy Timeline) 1 All Faculty (All Faculty list will display(diff. with our faculty and associated faculty) - No need of this, plz see the comments with their Profile pic,name, Course name(CA,CS,CMA),subject (Drop Down list)) 2. Main Faculty tab will have sub tab - All Faculties (with total number), then CA, CS, CMA tabs (Faculty will be sorted likewise). Faculty display box will have Faculty pic, name, course name (which he has authorized for that perticular academy by a faculty), subject dropdown (which he has authorized for that perticular academy by a faculty). |  | 8 | H |  | Madhukar | 2015-07-22 | 2015-07-22 | Not started | High | As discussed in task 13. Main Faculty tab will have sub tab - All Faculties (with total number), then CA, CS, CMA tabs (Faculty will be sorted likewise). Faculty display box will have Faculty pic, name, course name (which he has authorized for that perticular academy by a faculty), subject dropdown (which he has authorized for that perticular academy by a faculty). Please note - no need of diff. with our faculty associated faculty. This has been changed)
19) | a) Cart(Button) - (when user will click on this button,he will redirect to product page and he will add product from here.) This logic has been changed a bit. Plz see the comments. |  | 8 | H |  | Madhukar | 2015-07-23 | 2015-07-23 | Not started | High | When Academy will click on cart button, Academy will see the classes/products which has been approved by faculty for that perticular academy or center during its association request confirmation. Now academy/center can click on respective classes/products which will open in seperate window, then academy will add a details like class date, time, classroom capacity and hit publish button. Then this class will be displayed/published in academy classes tab.
20) | b) Remove(Button) Remove particular faculty. |  | 2 | H |  | Suraj | 2015-07-23 | 2015-07-23 | Not started | High | Okay
21) | c) Suggest(Button) (if user wants to suggest someone about this faculty/recommend this faculty.) |  | 6 | H |  | Suraj | 2015-07-23 | 2015-07-23 | Not started | Low | Hold this functionality for now
22) | d) Subject drop down list. |  | 5 | H |  | Suraj | 2015-07-24 | 2015-07-24 | Not started | High | okay
23) | Time Line: Posting will be deleted automaticaly after 90 days |  | 5 | m |  |  |  |  | Not started
24) | More Tab: File-> 1. Single file should not be more than 10 mb 2. If uploead file size greater than 150 mb, then it should not allow to upload more file until space is not empty.
25) | e) Notification This notification is on cart button. This means when faculty will add new classes/product to his profile for which that perticular academy is approved for, then this cart will get a notification on it. As well as it will be notified in timeline notifications. |  | 5 | H |  | Madhukar | 2015-07-24 | 2015-07-24 | Not started | High | This notification is on cart button. This means when faculty will add new classes/product to his profile for which that perticular academy is approved for, then this cart will get a notification on it. As well as it will be notified in timeline notifications.
26) | 5 Pending status (where Academy knows about pending request.) There are two pending request tabs (by Academy & By Faculty). You can see the pending requests in both tabs. However if Faculty send you a request Academy will have a confirm button or remove button and replay button. |  | 5 | H |  | Madhukar | 2015-07-24 | 2015-07-24 | Not started | High | There are two pending request tabs (by Academy & By Faculty). You can see the pending requests in both tabs. However if Faculty send you a request Academy will have a confirm button or remove button and replay button.
158
Total
| Switch Edusmart to Spring MVC + Mysql |  |  |  |  | Suraj/Madhukar | 2015-07-23

## Sheet1 (hidden)
|  |  |  | Sprint name: | 5 | 5
Start Date: 13-Jul-15 To 24-Jul-15
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold) | Priority | Client's comments
Time Line: Posting will be deleted automaticaly after 90 days
| More Tab: File-> 1. Single file should not be more than 10 mb 2. If uploead file size greater than 150 mb, then it should not allow to upload more file until space is not empty. | Total
Time Line: Posting will be deleted automaticaly after 90 days
More Tab: File-> 1. Single file should not be more than 10 mb 2. If uploead file size greater than 150 mb, then it should not allow to upload more file until space is not empty.

## Tools and Technologies
Sr. No. | Specification
Date :- 23-Jul-2015
Developement Environment Tools And Technologies
| Language | Java 1.7
| Framework | Spring 3.0, Hibernate 3.0,JPA , Tiles 2.1/SiteMesh
| RDBMS | My Sql 5.0
| Web Server | Apache Tomcat 7.0
| Editor & Other Tools | Eclipse Kepler 4.3/STS , SVN
| UI | HTML5, CSS3 , JavaScript.Jquery,Bootstrap
| Operating System | Windows 7

## Sprint 6
| List of Required steps for Migrating struts 2 to spring MVC 4 |  |  | Start Date | End Date
1 | Replace struts libraries with spring libraries (add dependencies). |  |  | 2015-07-23 | 2015-07-24
2 | Change made to web.xml file for struts to spring migration
3 | Replace config files for struts to spring migration
4 | Validation changes for struts to spring migration |  | Done | 2015-07-27 | 2015-08-01
5 | Tiles.xml : for controlling UI
6 | Hibernate configuration file : for database and pojo mapping
7 | Dispatcher-Servlet.xml : for take an incoming URI and find the right combination of handlers (generally methods on Controller classes) and views (generally JSPs) | acknowdge
8 | Pojo : Integrating pojo files
9 | JSP changes for struts to spring migration
| STRUTS | SPRING (corresponding tag)
| <html:html> | <html>
| <html:form> | <form:form>
| <html:error> | <form:errors>
| <html:text property="abc"> | <form:input path="abc">
| <html:select property="abc"> | <form:select path="abc">
| <option value="one"> | <option value="one">
| <html:submit> | <input type="submit">
| <bean:message bundle="resource" key="abc"> | <spring:message code="abc">
| <html:checkbox property="abc"> | <form:checkbox path="abc">
10 | TextArea Tag: |  |  | 2015-08-03 | 2015-08-07
| Struts<html:textarea> | Spring<form:textarea>
| property | path
| styleId | id
| styleClass | cssClass
| value | value
11 | Submit Button:-
| Struts<html:submit> | Spring<input type=”submit”
| styleClass | class | Done
| property | (Need to be remove)
| styleId | id
| value | value
| - | name
(assign same value as assign to value attribute)
12 | Hidden Field
| Struts<html:hidden> | Spring<form:hidden>
| property | path
| styleId | id
| styleClass | cssClass
| value | value
13 | TextBox
| Struts<html:text> | Spring<form:input>
| property | path
| styleId | id
| styleClass | cssClass
| value | value
14 | Form Tag
| Struts <html:form> | Spring<form:form>
| action | action
| styleId | id
| styleClass | class
| name | name
| - | commandName (Newly Added)
| method=post | method=post
| enctype="multipart/form-data" | enctype="multipart/form-data"
15 | Action class changes for struts to spring migration
| Struts action | Spring action
(corresponding replacement)
| extends Action | @controller annotation above class declaration
| public ActionForward execute( | @RequestMapping("/addStudent.do")
| ActionMapping mapping, | @RequestMapping(method = { RequestMethod.GET, RequestMethod.POST })
ActionForm form,
| HttpServletRequest request, | public ModelAndView execute (HttpServletRequest request, | Done
| HttpServletResponse response) | HttpServletResponse response,
| throws Exception { | @Valid@ModelAttribute("studentForm") studentForm studentForm,
BindingResult bindingResult)
throws Exception {
Here, in @RequestMapping annotation, action is getting mapped to corresponding action mentioned in jsp.
And in @ModelAttribute annotation, form is getting mapped which should be same as that of mentioned in commandName in jsp.
| forward = mapping.findForward(“success”); | modelMap.put("studentForm", studentForm);
return (newModelAndView(“success”,modelMap));

## Sprint 7
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold)
| Faculty Tab: Time Line: a)Faculty Registration b) Validation Part |  | 8 |  |  | madhukar/suraj | 2015-08-10 | 2015-08-14 | Done
| A)Add Faculty: I)List of all Faculty(Search functionality -Faculty). |  | 8 |  |  | madhukar/suraj
| 2)List of course level of selected faculty with check box. |  | 5 |  |  | madhukar/suraj |  |  | Madhukar WIP
| 3) Send email to selected Faculty |  | 5 |  |  | madhukar/suraj
| B)Pending Status (Faculty list) of Categorised faculty till Accepted the request. |  | 9 |  |  | madhukar/suraj
| C) Display List of all faculty 1) Display List of all CA |  | 4 |  |  | madhukar/suraj
| 2) Display List of all CMA display in tiles |  | 3 |  |  | madhukar/suraj
| 3) Display List of all CS display in tiles |  | 4 |  |  | madhukar/suraj
| 2) Student tab : Display Student List 2) Display List of all CA display in tiles 2) Display List of all CSdisplay in tiles 2) Display List of all CMA display in tiles |  | 6+2 |  |  | madhukar/suraj
| Student Search Functionality of students |  | 8+1 |  |  | madhukar/suraj
| About Tab(Faculty) 1) Description Add Description |  | 3 |  |  | madhukar/suraj |  |  | WIP
| 2)Edit Description(Update Functionality) |  | 3 |  |  | madhukar/suraj |  |  | WIP
| 3)Reset Description 4)Delete Description |  | 5 |  |  | madhukar/suraj
| 2) Information 1) Add Information 2) Edit Information |  | 6 |  |  | madhukar/suraj
| 3)Reset Information 4) Delete Information |  | 5 |  |  | madhukar/suraj
| Right SideBar(Faculty) 1)News List |  | 4 |  |  | madhukar/suraj |  |  | Done
| 2) Upcoming Events |  | 4 |  |  | madhukar/suraj |  |  | Done
| while delete,generate confirmetion popup |  | 4 |  |  | madhukar/suraj |  |  | Done

## Sprint6 (hidden)
Start Date: 20-jul-15 To 24-jul-15
No. of Story | Features / Functionality Description | Size (XS / S / M / L / XL / XXL / XXXL) | Estimated Man Hours (2 / 4/ 8 / 16 / 24 / 32 / 40 ) hrs | Priority (H / M / L) | Sprint no in which story will be picked up | Development owner (name of the developer / Tester) | Start Date | End Date | Status (Done / WIP / Not started / On Hold)
1) | Create Faculty (create a new faculty.) a) personal account info. (form) |  | 5 | H |  | Suraj/Madhukar | 2015-07-20 | 2015-07-20
2) | Recently Added (Display recently added faculty list) |  | 8 | H |  | Suraj/Madhukar | 2015-07-20 | 2015-07-21
3) | b) faculty account info. (form) |  | 5 | H |  | Suraj/Madhukar | 2015-07-22 | 2015-07-22
4) | c) table designing |  | 4 | H |  | Suraj/Madhukar | 2015-07-22 | 2015-07-22
5) | 4 Add Faculty (Faculty which is already in database,Academy will send a request through mail to join his Academy.) pop up will be generated with field like faculty name and email address. |  | 16 | H |  | Suraj/Madhukar | 2015-07-20 | 2015-07-21
6) | Faculty Tab (Academy Timeline) 1 All Faculty (All Faculty list will display(diff. with our faculty and associated faculty) with their Profile pic,name, Course name(CA,CS,CMA),subject (Drop Down list)) |  | 8 | H |  | Suraj/Madhukar | 2015-07-22 | 2015-07-22
7) | a) Cart(Button) (when user will click on this button,he will redirect to product page and he will add product from here.) |  | 8 | H |  | Suraj/Madhukar | 2015-07-23 | 2015-07-23
8) | b) Remove(Button) Remove particular faculty. |  | 5 | H |  | Suraj/Madhukar | 2015-07-23 | 2015-07-23
9) | c) Suggest(Button) (if user wants to suggest someone about this faculty/recommend this faculty.) |  | 6 | H |  | Suraj/Madhukar | 2015-07-23 | 2015-07-23
10) | d) subject drop down list. |  | 5 | H |  | Suraj/Madhukar | 2015-07-23 | 2015-07-23
11) | e) notification |  | 5 | H |  | Suraj/Madhukar | 2015-07-23 | 2015-07-23
12) | 5 Pending status (where Academy knows about pending request.) |  | 5 | H |  | Suraj/Madhukar | 2015-07-24 | 2015-07-24
80